## Sheet1
Thorseby Vale, Edwinstowe - Indicative s106 cashflow - DRAFT | [18 empty] | EC060918
| Year | 2019 |  | 2020 | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024
| Phase 1 | Phase 1
| Phase 2 |  |  | Phase 2
| Phase 3 |  |  |  |  | Phase 3
| Phase 4 | [12 empty] | Phase 4
Phase 5
Phase 6
Phase 7
| Units/ Trigger | Commencement of development on the Agricultural Tenancy Land | 60 | 90 | 150 | 151 | 180 | 250 | 270 | 300 | 40% (320) | 40% (320) | 360 | 400 | 450 | 60% (480) |  | 800 | Total
Item | [18 empty] | 0
Community Facilities |  |  |  | 50000 |  | 250000 | [12 empty] | 300000
Child and Youth Play Space |  |  |  | 50000 | [14 empty] | 50000
Sports Pitch |  |  |  | 196725.33 | [5 empty] | 196725.33 |  |  |  |  | 196725.33 |  |  |  | 590175.99
Healthcare |  |  |  | 157219.2 |  |  | 157219.2 |  | 157219.2 |  |  |  | 157219.2 |  | 157219.2 |  |  |  | 786096
Library |  |  |  | 17565 |  |  | 17565 | [11 empty] | 35130
Bus Stop |  |  |  | 54000 | [14 empty] | 54000
Off site highways | [5 empty] | 25000 | [12 empty] | 25000
Ollerton Roundabout | [5 empty] | 1100000 | Timing of Payment to be agreed | [11 empty] | 1100000
Sub Total |  |  | 0 | 525509.53 | 0 | 1375000 | 174784.2 | 0 | 157219.2 | 196725.33 | 0 | 0 | 157219.2 | 0 | 353944.53 | 0 | 0 | 0 | 2940401.99
Viability Review
Education 1 |  | Notify LPA of decision Option 1 or 2 If Option 2 £365,000 payable prior to first occupation |  | Submit Scheme to NCC for approval 18 month lead in required to prepare detailed design proposals | Submit Planning Application and undertake school site remediation and enabling Infrastructure works | Commence Construction |  |  | Complete construction and transfer within 3 months post practical completion
Education 2 |  |  |  |  | Undertake School site remediation and enabling infrastructure works | 1620000 | 1620000 | NCC to have secured planning, discharged the Ollerton R'about condition prior to serving notice. This represents the earliest the contributions can be made. Proposed NCC to match timescales | [10 empty] | 3600000
6540401.99